## Sheet1
User story | Task | WIP? | Done? | Who?
Website is formatted more nicely to more pleasantly display the information to the user | Making style sheets | Y | N | JM
| Reformatting html views | Y | N | JM
| Formating quest listing page | Y | N | NB
| Formating quest info page | Y | N | NB
| Formating quest result page | N | N | NB
| Formating Discusssion pages | N | N
| Formating login page | N | N
| Formating shop page | N | N
| Formating forge page | N | N
| Formating profile page | N | N
User can direct message other players to collaborate | Messaging system | Y | N | Reza
Selling items | Method of selling items |  | Y | JI
| Sold items appear in shop |  | Y | JI
| Not-sold items DON'T appear in shop |  | Y | JI
User can update cost to hire | Profile page has cost to hire update form |  | Y | JI
Unity game stuff
User can use special abilities depending on their highest stat | special button changes names |  | Y | JI
| CRASH |  | Y | JI
| BOLSTER |  | Y | JI
| PREPARE |  | Y | JI
GUARD actually blocks | Implementing blocking |  | Y | JI
Database communication | Communicating with the database | Y | N | JI